## Inception
Development Team | Project Manager
Systems Analyst
Software Architect
Test Manager
Assessment 1 - Inception iteration
Document / Deliverable | Sections / Task
Project Management | MS Project - Setup project and schedule tasks
Create Project Plan
Group Guidelines & Task Assignment
Requirements | Vision Document
System Wide Requirements
Use Case Diagram
Confirm requirements with Client
Update Requirements & Client Sign off

## Elaboration
Elaboration Iteration
Document / Deliverable | Sections / Task
Project Management | Review Progress, update MS Project (Task completion data, Reports)
Team Meetings
Review Risk aspects
Requirements | Use Case Specicifications for Version 1 application
Develop Requirements Traceability Matrix
Designs | User Interface Designs - Version 1 Applications
Development | Set up Development Environment
Develop Libraries of functions (for use in many programs)
Develop Prototype of Web application
Prototype of Mobile apps
Testing | Test Prototypes
User Consultation | Review Use Case Specifications and Prototypes with client
Feedback | Update Requirements and Prototypes (based on Feedback

## Construction 1
Construction 1 Iteration
Document / Deliverable | Sections / Task
Project Management | Review Progress, update MS Project (Task completion data, Reports)
Team Meetings
Review Risk aspects
Requirements | Use Case Specicifications for Version 2 application
Update Requirements Traceability Matrix
Designs | User Interface Designs - Version 2 Applications
Development Version 1 Web Application | Web pages to Add, Edit, Update, Delete a Student
Web pages to Add, Edit, Update, Delete a Subject
etc…….
Development Version 1 Mobile Application | Head to Head Challenge - Mobile app Level 1
Wordgames- Mobile app Level 1
Updates and Debugging (after testing)
Testing | Integration Testing, Version 1 Web site
Integration Testing, Mobile Applications level 1 games
User Acceptance Testing - Version 1 Applications
Regression testing (after debugging and updates)
User Consultation | Review Use Case Specifications for Version with the client
Feedback | Update Requirements and Prototypes (based on Feedback

## Construction 2
Construction 2 Iteration
Document / Deliverable | Sections / Task
Project Management | Review Progress, update MS Project (Task completion data, Reports)
Team Meetings
Review Risk aspects
Requirements | Update Requirements Traceability Matrix
Designs | Report designs
Development Version 2 Web Application | Web pages to Add, Edit, Update, Delete Topics
Web pages to Add, Edit, Update, Delete Questions
etc…….
Development Version 2 Mobile Application | Head to Head Challenge - Mobile app Level 2
Wordgames- Mobile app Level 2
Head to Head Challenge - Mobile app Level 3
Wordgames- Mobile app Level 3
Updates and Debugging (after testing & feedback)
Testing | Integration Testing, Version 2 Web site
Integration Testing, Mobile Applications level 2 games
Integration Testing, Mobile Applications level 3 games
User Acceptance Testing - Version 2 Applications
Regression testing (after debugging and updates)
User Consultation | review Web and Mobile applications with the client
Feedback | Update Web site and Mobile Applications based on Feedback

## Transition
Transition Iteration
Document / Deliverable | Sections / Task
Project Management | Review Progress, update MS Project (Task completion data, Reports)
Team Meetings
Review Risk aspects
Update Requirements Traceability Matrix
Project Closure Reporting
Finalize Applications | Finalize outstanding issues with Web site
Finalize outstanding issues with Head to Head challenge Mobile App
Finalize outstanding issues with Wordgames Mobile App
Updates and Debugging (after testing & feedback)
Testing | System Testing - Web Application
System Testing - Head to Head challenge Mobile App
System Testing - Wordgames Mobile App
User Acceptance Testing - Final System
Regression testing (after debugging and updates)
User Consultation | Review final Web and Mobile applications with the client
Feedback | Update Web site and Mobile Applications based on Feedback
Handover | Demonstrate the working system to the client
Installation of system on Clients Server
Deploy mobile apps to Playstore and app store